## Executive Summary
ACQC Upgrade Readiness — Executive Summary
Upgrade Risk Index (URI)
URI Score | 100 / 100
Grade | F — Critical risk — major upgrade blockers present
Engineering Hours | 206h
QA Hours | 83h
Infra Hours | 30h
Total w/ Contingency | 399h
Recommended Timeline | 6–8 weeks
Earliest Go-Live | 2026-06-07
Issue Summary
AC Version | 2.4.5 → 2.4.8
Total Issues | 3
Critical | 3
High | 0
Medium | 0
Low | 0

## Sprint Plan
Sprint | Sprint Name | Finding ID | File | Message | Severity | Est Hours | Owner
1 | Critical Blockers & Upgrade Prerequisites | F-0001 | InstallSchema.php | Legacy setup script found: InstallSchema implements Magento\Framework\Setup\InstallSchemaInterface. Migrate to db_schema.xml + DataPatch. | Error | 48
1 | Critical Blockers & Upgrade Prerequisites | F-0002 | UpgradeData.php | Legacy setup script found: UpgradeData implements Magento\Framework\Setup\UpgradeDataInterface. Migrate to db_schema.xml + DataPatch. | Error | 48
2 | High-Effort Remediation | — |  |  |  | 0
3 | Warnings & Low-Effort Fixes | F-0004 | InstallSchema.php | Setup scripts deprecated - use declarative schema | Critical | 0
3 | Warnings & Low-Effort Fixes | F-0005 | UpgradeData.php | UpgradeData deprecated - use data patches | Critical | 0
3 | Warnings & Low-Effort Fixes | F-0006 | UpgradeData.php | Direct database query | Critical | 0
3 | Warnings & Low-Effort Fixes | F-0007 | db_schema.xml | Module Vendor/ModernModule has db_schema.xml but no db_schema_whitelist.json. Upgrade will fail without whitelist. | Error | 2
3 | Warnings & Low-Effort Fixes | F-0008 |  | Adding index to large table catalog_product_entity_varchar in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Warning | 0
3 | Warnings & Low-Effort Fixes | F-0009 |  | Dropping column weee_tax_applied_row_amount from large table quote_item in AC 2.4.8 requires a maintenance window. | Error | 16
3 | Warnings & Low-Effort Fixes | F-0010 |  | Adding index to large table sales_order in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Warning | 0
3 | Warnings & Low-Effort Fixes | F-0011 |  | Dropping column tax_before_discount from large table quote_item in AC 2.4.8 requires a maintenance window. | Error | 16
3 | Warnings & Low-Effort Fixes | F-0012 |  | Adding index to large table catalog_product_entity in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Warning | 0
3 | Warnings & Low-Effort Fixes | F-0013 |  | Dropping column weee_base_tax_applied_row_amnt from large table sales_order_item in AC 2.4.8 requires a maintenance window. | Error | 16
3 | Warnings & Low-Effort Fixes | F-0014 |  | Adding index to large table cataloginventory_stock_item in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Warning | 0
3 | Warnings & Low-Effort Fixes | F-0015 |  | Dropping column tax_before_discount from large table quote_item in AC 2.4.8 requires a maintenance window. | Error | 16
3 | Warnings & Low-Effort Fixes | F-0016 |  | Adding unique index to large table catalog_product_entity in AC 2.4.8 requires full table scan. Plan maintenance window. | Error | 24
3 | Warnings & Low-Effort Fixes | F-0017 |  | Adding index to large table catalog_category_product_index in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Warning | 0
3 | Warnings & Low-Effort Fixes | F-0018 |  | Adding index to large table catalog_product_entity_varchar in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Warning | 0
3 | Warnings & Low-Effort Fixes | F-0019 |  | AC 2.4.8 requires PHP extension ext-xsl which is not declared in composer.json config.platform. | Warning | 0
4 | QA Hardening & Regression Testing | — |  |  |  | 29

## Full Issue Register
ID | File | Line | Module | Severity | Type | Message | Est Hours | Owner
F-0001 | tests/Fixtures/UpgradeReadiness/LegacyProject/app/code/Vendor/LegacyModule/Setup/InstallSchema.php | 12 | Vendor/LegacyModule | Critical | deprecated | Setup scripts deprecated - use declarative schema | —
F-0002 | tests/Fixtures/UpgradeReadiness/LegacyProject/app/code/Vendor/LegacyModule/Setup/UpgradeData.php | 11 | Vendor/LegacyModule | Critical | deprecated | UpgradeData deprecated - use data patches | —
F-0003 | tests/Fixtures/UpgradeReadiness/LegacyProject/app/code/Vendor/LegacyModule/Setup/UpgradeData.php | 18 | Vendor/LegacyModule | Critical | security | Direct database query | —

## DB Risk Register
Table / File | Change Type | Migration Risk | Message | Recommendation
InstallSchema.php | legacy_setup_script_detected | Error | Legacy setup script found: InstallSchema implements Magento\Framework\Setup\InstallSchemaInterface. Migrate to db_schema.xml + DataPatch. | 1. Create etc/db_schema.xml with declarative schema. 2. Replace data scripts with Setup/Patch/Data classes implementing DataPatchInterface. 3. Generate db_schema_whitelist.json with: bin/magento setup:db-declaration:generate-whitelist --module-name=VendorModule. See: https://developer.adobe.com/commerce/php/development/components/declarative-schema/
UpgradeData.php | legacy_setup_script_detected | Error | Legacy setup script found: UpgradeData implements Magento\Framework\Setup\UpgradeDataInterface. Migrate to db_schema.xml + DataPatch. | 1. Create etc/db_schema.xml with declarative schema. 2. Replace data scripts with Setup/Patch/Data classes implementing DataPatchInterface. 3. Generate db_schema_whitelist.json with: bin/magento setup:db-declaration:generate-whitelist --module-name=VendorModule. See: https://developer.adobe.com/commerce/php/development/components/declarative-schema/
db_schema.xml | db_schema_whitelist_missing | Error | Module Vendor/ModernModule has db_schema.xml but no db_schema_whitelist.json. Upgrade will fail without whitelist. | Run: bin/magento setup:db-declaration:generate-whitelist --module-name=Vendor/ModernModule
catalog_product_entity_varchar | large_table_index_add_warning | Warning | Adding index to large table catalog_product_entity_varchar in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Verify MySQL supports online DDL for this operation. Use ALGORITHM=INPLACE,LOCK=NONE when possible.
quote_item | large_table_column_drop_risk | Error | Dropping column weee_tax_applied_row_amount from large table quote_item in AC 2.4.8 requires a maintenance window. | Schedule a maintenance window. Consider pt-online-schema-change or gh-ost for zero-downtime DDL.
sales_order | large_table_index_add_warning | Warning | Adding index to large table sales_order in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Verify MySQL supports online DDL for this operation. Use ALGORITHM=INPLACE,LOCK=NONE when possible.
quote_item | large_table_column_drop_risk | Error | Dropping column tax_before_discount from large table quote_item in AC 2.4.8 requires a maintenance window. | Schedule a maintenance window. Consider pt-online-schema-change or gh-ost for zero-downtime DDL.
catalog_product_entity | large_table_index_add_warning | Warning | Adding index to large table catalog_product_entity in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Verify MySQL supports online DDL for this operation. Use ALGORITHM=INPLACE,LOCK=NONE when possible.
sales_order_item | large_table_column_drop_risk | Error | Dropping column weee_base_tax_applied_row_amnt from large table sales_order_item in AC 2.4.8 requires a maintenance window. | Schedule a maintenance window. Consider pt-online-schema-change or gh-ost for zero-downtime DDL.
cataloginventory_stock_item | large_table_index_add_warning | Warning | Adding index to large table cataloginventory_stock_item in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Verify MySQL supports online DDL for this operation. Use ALGORITHM=INPLACE,LOCK=NONE when possible.
quote_item | large_table_column_drop_risk | Error | Dropping column tax_before_discount from large table quote_item in AC 2.4.8 requires a maintenance window. | Schedule a maintenance window. Consider pt-online-schema-change or gh-ost for zero-downtime DDL.
catalog_product_entity | large_table_unique_index_risk | Error | Adding unique index to large table catalog_product_entity in AC 2.4.8 requires full table scan. Plan maintenance window. | Use pt-online-schema-change or gh-ost to add the unique index without locking the table.
catalog_category_product_index | large_table_index_add_warning | Warning | Adding index to large table catalog_category_product_index in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Verify MySQL supports online DDL for this operation. Use ALGORITHM=INPLACE,LOCK=NONE when possible.
catalog_product_entity_varchar | large_table_index_add_warning | Warning | Adding index to large table catalog_product_entity_varchar in AC 2.4.8. Consider ALGORITHM=INPLACE,LOCK=NONE. | Verify MySQL supports online DDL for this operation. Use ALGORITHM=INPLACE,LOCK=NONE when possible.

## Composer Audit
Package | Issue Type | Installed Version | Fix / Replacement
| platform_extension_missing | — | AC 2.4.8 requires PHP extension ext-xsl which is not declared in composer.json config.platform.

## Effort Estimate
Effort Estimate
Category | Hours | Notes
Engineering | 206 | Code remediation, refactoring, and migration
QA / Testing | 83 | Test plan execution, regression, and UAT
Infrastructure | 30 | Env setup, staging, pipeline updates
Contingency (25%) | 80 | Buffer for unknowns and re-work
Total | 399

## Timeline Projection
Timeline Projection
Recommended Timeline | 6–8 weeks
Earliest Go-Live | 2026-06-07
URI Grade | F — Critical risk — major upgrade blockers present
Total Hours (w/ contingency) | 399h
Sprint Plan
Sprint | Name | Findings | Hours
1 | Critical Blockers & Upgrade Prerequisites | 2 | 96
2 | High-Effort Remediation | 0 | 0
3 | Warnings & Low-Effort Fixes | 16 | 90
4 | QA Hardening & Regression Testing | 0 | 29

## Module Heatmap
Module Risk Heatmap
Module | Total Findings | Errors | Warnings | Est. Hours
Vendor/LegacyModule | 3 | 3 | 0 | 0

## Issues by Priority
Priority | Count | Percentage
Critical | 3 | 100%
High | 0 | 0%
Medium | 0 | 0%
Low | 0 | 0%

## Effort Breakdown
Component | Hours | Percentage
Development | 26 | 23.5%
Testing | 24 | 21.7%
Code Review | 11.1 | 10%
Buffer | 16.6 | 15%
Total | 110.5 | 100%